FORWARD DEPLOYED AI ENGINEERING

Capstone Project — CloudServe Solutions

Stage 4: Sprint Plan

Completed by: Rajarajan Venkatesan  |  Planned 8 September 2026  |  Review milestone 15 September  |  Submission deadline 20 September 2026, 23:59

Why this plan has two phases.  Stages 1 to 3 are complete as of 8 September. The remaining work is planned in two phases rather than one, because the project is reviewed with the course coordinator before it is submitted. Phase A, 8 to 15 September, produces a working system that has cleared the gate together with the evidence to discuss it — that is the state the review needs. Phase B, 16 to 20 September, turns that into the submitted artefact: report, video and package, with whatever the review surfaces folded in. The gate is scheduled to clear on 14 September, one day before the review, so the conversation is about measured results rather than about intentions.

# 1. Capacity

Honest capacity, not optimistic capacity. This project runs alongside full-time work, so weekday availability is limited to evenings and the weekend days carry most of the build.

| Phase | Dates | Hours available | What it must produce |
| --- | --- | --- | --- |
| Phase 0 — complete | to 8 Sept | ~14 hrs, already spent | Discovery workbook, PRD v1, prompt library, repo scaffold with the harness CLI contract already proven |
| Phase A — build, gate, measure | Tue 8 – Tue 15 Sept | ~31 hrs (six weekday evenings at ~2.5 hrs, two weekend days at ~8 hrs) | A system that has processed the full validation set unattended, with a metrics report, a reconciled decision log, and a passing test suite — enough to review on merit |
| Coordinator review | 15 Sept onward | — | Discussion held against a working system and real numbers, not against a plan |
| Phase B — present and submit | Wed 16 – Sun 20 Sept | ~21 hrs | PRD revision, governance framework, report PDF, video, packaged archive |

Phase A capacity is roughly 31 hours against a Phase A backlog of roughly 34 hours. The three-hour deficit is real and is what Section 5 resolves. Phase B is approximately 21 hours against a 21-hour backlog, with no slack — which is why nothing from Phase A is allowed to drift into it.

What Stage 3 already bought back.  The four build prompts were written during Stage 3, before the build began. On the classifier, the generator and the guardrail, the prompt is the substantive design work and the surrounding code is comparatively mechanical. The estimates below reflect that — those three items are costed at roughly three hours each rather than four, and that saving is the only reason Phase A fits at all.

# 2. The backlog

Estimates in hours so they can be compared against capacity. Priority decides what survives when time runs short: Must means the project fails the gate or an acceptance criterion without it; Should means expected but deferrable with a stated consequence; Could means it adds value if time allows.

| ID | Item | Est. hrs | Priority | Phase | Definition of done |
| --- | --- | --- | --- | --- | --- |
| B-01 | Environment, key, and a real model call | 1.5 | Must | A | venv active, requirements installed, OpenRouter key in .env, and a live call returns real text |
| B-02 | Ingest and normalisation, four channels | 3 | Must | A | A ticket from each channel prints as a normalised object; empty body and missing subject do not raise (A2) |
| B-03 | Chunking and embedding the corpus | 2 | Must | A | Corpus embedded and persisted; two chunk configurations compared and the better one recorded with its justification |
| B-04 | Vector store and retrieval | 2 | Must | A | A known question returns the right passage and its doc_id resolves into documentation.json (A4); an irrelevant query returns nothing |
| B-06 | Intent and urgency classifier | 2.5 | Must | A | Every ticket returns a class and a confidence in [0,1]; a contentless ticket returns unclear_request rather than raising (A3) |
| B-07 | Routing logic and threshold | 2.5 | Must | A | Threshold derived from development data and written down with its justification; same ticket twice yields the same decision (A5); never-automate list enforced (FR-08) |
| B-10 | Decision logging wired through | 1.5 | Must | A | Every stage writes a row; logged decisions reconcile against tickets processed with no gaps (A8) |
| B-08 | Answer generation with citations | 3 | Must | A | Citations resolve to passages actually retrieved (A6); tickets with no documentation coverage return answer_possible=false |
| B-09 | Guardrails, both layers | 3 | Must | A | Deterministic rules plus PR-05; an engineered ticket is blocked rather than sent, and checks_performed is logged either way (A7) |
| B-05 | Harness computing real metrics | 3 | Must | A | Volume, business, technical and governance figures computed for real, replacing the current placeholder nulls (A10) |
| B-11 | Full unattended run — THE GATE | 4 | Must | A | Started once, left alone, processes the full validation set, produces a metrics report, no intervention (A9) |
| B-18 | Test suite | 1.5 | Must | A | pytest runs with one documented command and passes, covering the TC-01 to TC-13 cases named in Stage 3 (A12) |
| B-19 | Clean-checkout verification | 1 | Must | A | Repository cloned into an empty directory and the README followed literally, without improvisation (A1) |
| B-14 | Fairness segmentation | 1 | Should | A | Quality and citation accuracy segmented by customer_tier, customer_region and language_fluency (NFR-06) |
| B-16 | PRD revision and Stage 5 revision log | 2 | Must | B | At least one substantive requirement change recorded with the trigger that caused it — this revision is compulsory |
| B-17 | Governance framework | 3 | Must | B | Risk register, incident procedure and kill switch complete; decision-log schema documented |
| B-13 | Continuous integration pipeline | 1.5 | Should | B | GitHub Actions workflow runs pytest on push and passes |
| B-15a | Report | 6 | Must | B | One PDF in the prescribed section order, numbers interpreted rather than listed, AI-use declaration included |
| B-15b | Video | 6 | Must | B | 18–22 minutes, two takes, including 7 minutes of live demonstration with a success, an escalation, a guardrail blocking, and the unattended run |
| B-15c | Submission package | 2 | Must | B | Archive named FirstnameLastname_Capstone_Submission.zip with exactly four folders, checked against the pack's final checklist |
| B-12 | Monitoring and dashboards | 3 | Could | B | Prometheus metrics exposed; Grafana dashboard showing throughput, outcome split, latency and guardrail activations |

Phase A total: 31.5 hours against ~31 available. Phase B total: 23.5 hours against ~21 available, of which B-12 is the three hours designated to go first.

# 3. Phase A in detail — build, gate and measure (8 to 15 September)

Sequenced so retrieval and the harness land early, per the pack's planning rules. The daily targets map onto the Build Specification's own week-two checkpoints, compressed into the time actually available.

| Day | Hrs | What will be finished by the end of the day | Risk to this |
| --- | --- | --- | --- |
| Tue 8 Sept | 2.5 | B-01, and B-02 begun. Environment working with a live model call returning real text. | OpenRouter signup or a stray newline in the key eats the evening. Mitigated by doing the key check first, before writing any pipeline code |
| Wed 9 Sept | 2.5 | B-02 complete. A ticket from each of the four channels prints normalised. Build Spec Day 1 checkpoint met. | Chat tickets carry an empty subject and some bodies contain unusual characters; both are known from the dataset, so they are handled now rather than discovered during the gate run |
| Thu 10 Sept | 2.5 | B-03. Corpus chunked and embedded, two configurations compared. | The first embedding run downloads the model and is slow. Start that download before anything else so it caches while the chunking code is written |
| Fri 11 Sept | 2.5 | B-04 complete, B-06 begun. Retrieval returns traceable passages; an irrelevant query returns nothing. Build Spec Day 2 checkpoint met. | Chroma silently returns zero results if the store is read from a different path than it was written to. Use an absolute path from configuration in both places |
| Sat 12 Sept | 8 | B-06, B-07, B-10, and B-08 begun. Classification, routing and logging working end to end; twenty tickets run and the log read, every decision carrying a reason. Build Spec Day 3 checkpoint met. | Threshold derivation is analysis rather than coding and can absorb an afternoon. Timebox it to one hour, record the chosen value with its justification, and move on |
| Sun 13 Sept | 8 | B-08, B-09, B-05. Cited answers produced, both guardrail layers blocking, harness computing real metrics. Build Spec Day 4 checkpoint met. | The heaviest day. If generation slips, guardrails cannot be tested and the gate is at risk — this is the day to protect above all others |
| Mon 14 Sept | 2.5 | B-11. Full validation set processed unattended in a single run, producing a metrics report. THE GATE CLEARS. | Rate limiting across 80 consecutive tickets on a free tier is the most likely failure. Backoff and response caching are built on Sunday as part of B-05, not retrofitted here |
| Tue 15 Sept | 2.5 | B-18, B-19, B-14. Tests passing under one command, clean checkout verified, fairness figures segmented. Ready for the coordinator review. | Clean-checkout verification routinely exposes a missing pin or an undocumented step. That is the point of doing it here, with five days still in hand rather than on the final weekend |

The rule for Phase A.  If Saturday 12 September ends without routing and logging working, scope is cut rather than the gate being moved. A system that handles a reduced set of intent categories properly and processes the full set unattended passes. A system that handles all twenty-two beautifully but has never run more than five tickets in sequence does not.

# 4. Phase B in detail — present and submit (16 to 20 September)

Begins from a system that already works and has already been measured, so nothing here depends on a build succeeding. Coordinator feedback from the 15 September review is folded in on the Friday.

| Day | Hrs | What will be finished by the end of the day | Risk to this |
| --- | --- | --- | --- |
| Wed 16 Sept | 2.5 | B-16. PRD revised and the Stage 5 revision log completed, with at least one substantive change and the trigger that caused it. | Low risk. The material comes from what the build actually taught, which by now exists as evidence rather than as recollection |
| Thu 17 Sept | 2.5 | B-17. Governance framework complete: risk register, incident procedure, kill switch. | Much of this derives from the risk register already drafted in the discovery workbook, so it is an expansion rather than a blank page |
| Fri 18 Sept | 3 | Report drafted in the prescribed section order. Coordinator feedback incorporated. B-13 if time allows. | Writing the evaluation interpretation is slower than expected. The figures themselves are already produced by the harness, which removes the usual bottleneck |
| Sat 19 Sept | 8 | B-15b. Video recorded twice — first take to find what cannot yet be explained cleanly, second take for submission. | The first take always overruns twenty-two minutes. Budgeting the whole day for two takes is the mitigation, exactly as the pack advises |
| Sun 20 Sept | 6 | B-15a, B-15c. Report finalised as one PDF. Archive assembled, named correctly, checked against the pack's final checklist. Submitted before 23:59. | No building on this day by design. Anything still unbuilt on Sunday morning is cut rather than attempted |

# 5. What will be dropped if time runs short

Phase A exceeds its capacity by roughly half an hour and Phase B by roughly two and a half, so something on this list is likely to go. Deciding the order now protects what carries the most marks — and every item here sits outside the twelve acceptance criteria, which is precisely why it is on this list rather than in the plan.

| Item | Cut order | Consequence of cutting it | What will be said about it in the report |
| --- | --- | --- | --- |
| B-12 Grafana dashboards, keeping the Prometheus metrics endpoint | 1st to go | Monitoring is described in the Setup Guide but appears in none of the twelve acceptance criteria. The metrics endpoint alone still demonstrates the instrumentation. | That metrics are exposed and scrapeable, that the dashboard was descoped deliberately under a compressed timeline, and what it would have shown — the confidence-score distribution being the one that matters, since drift appears there first |
| Full 22-class intent coverage, reduced to the highest-volume classes plus unclear_request as the fallback | 2nd to go | Lower classification coverage. The Build Specification states explicitly that a system handling a reduced set properly and running unattended passes, while a broad but fragile one does not. | Which classes were kept and why, what the fallback does with the remainder, and the measured effect on the escalation rate — presented as a scope decision with a stated cost, not as an omission |
| B-13 continuous integration pipeline | 3rd to go | The test suite still runs and passes locally under one documented command, which is what A12 requires. CI is good practice the Setup Guide asks for, but it is not an acceptance criterion. | That tests run and pass under a single command, and that the CI workflow was descoped rather than faked with a workflow file that was never observed to run green |
| B-14 fairness segmentation narrative, keeping the segmented figures themselves | 4th to go | Governance carries 10% and fairness is named explicitly, so this is reduced rather than removed. The numbers still get reported; only the interpretation thins. | The segmentation as measured, with an honest statement that the interpretation is thinner than intended and what further analysis would be required to draw a conclusion from it |
| Second video take | 5th to go | Communication carries 10% and a single unrehearsed take is noticeably weaker. Last in the order precisely because the pack warns this is the most commonly underestimated deliverable. | Nothing. A weaker video speaks for itself. It is listed here to make explicit that it is the final thing to sacrifice, not a planned economy |

What will not be cut, under any circumstances.  The full unattended run (B-11), the decision log (B-10), the blocking guardrail (B-09), the test suite (B-18), the compulsory PRD revision (B-16), and clean-checkout verification (B-19). The first four are acceptance criteria or gate conditions, the fifth is compulsory, and the sixth is the step at which roughly half of all submissions are reported to fail.

# 6. Daily check-in record

Ten minutes at the start of each day, three questions. Kept as the project runs rather than reconstructed afterwards — a log written from memory in the final week is both inaccurate and obvious, and this record is what makes the effort log and the report's reflection section truthful.

| Date | Finished since yesterday | Doing today | Blocked by |
| --- | --- | --- | --- |
| Tue 8 Sept | Stage 1 discovery workbook, Stage 2 PRD v1, Stage 3 prompt library, repo scaffold with the harness CLI contract already proven against an arbitrary input path | B-01 environment and a live model call; B-02 ingest begun | Nothing |
| Wed 9 Sept |  |  |  |
| Thu 10 Sept |  |  |  |
| Fri 11 Sept |  |  |  |
| Sat 12 Sept |  |  |  |
| Sun 13 Sept |  |  |  |
| Mon 14 Sept |  |  |  |
| Tue 15 Sept |  |  |  |
| Wed 16 Sept |  |  |  |
| Thu 17 Sept |  |  |  |
| Fri 18 Sept |  |  |  |
| Sat 19 Sept |  |  |  |
| Sun 20 Sept |  |  |  |