FORWARD DEPLOYED AI ENGINEERING

Capstone Project — CloudServe Solutions

Effort Log

How this log was kept.  Entries were recorded as the work happened, in LEARNING_LOG.md and PROGRESS.md, both of which are committed to the repository with timestamps that predate this document. This log is assembled from those daily records rather than reconstructed from memory at the end, and the commit history is the evidence for that. Hours are actual hours worked, including the four on Tuesday 15 September that produced nothing assessable.

# 1  Details

| Field | Value |
| --- | --- |
| Full name | Rajarajan Venkatesan |
| Project start date | 6 September 2026 |
| Target submission date | 20 September 2026, 23:59 |
| Coordinator review | 15 September 2026 — five days before submission, by arrangement |
| Hours available per week | Roughly 21 to 26. The project runs alongside full-time work: weekday evenings at about 2.5 hours, weekend days at about 8 |
| Total hours recorded | 79.5 — of which 71.5 worked and 8.0 planned (video and packaging) |

# 2  Summary of hours by stage

Completed last, from the daily entries below. The totals reconcile with those entries.

| Stage | Planned | Actual | Difference | Why the difference |
| --- | --- | --- | --- | --- |
| 0. Orientation | 1.0 | 2.0 | +1.0 | Reading the pack end to end and mapping the twelve acceptance criteria onto the four submission parts. Double the estimate and worth it — nothing later was built against a guess about what is graded |
| 1. Discovery | 6.0 | 8.0 | +2.0 | The analysis scripts took longer than the write-up. Cross-tabulating intent against answerability was not in the plan and is the single most valuable half-hour in the project |
| 2. Requirements | 3.0 | 3.0 | 0 | On estimate. The only stage that landed exactly, and only because discovery had already done the thinking |
| 3. Prompt library | 2.5 | 2.5 | 0 | On estimate |
| 4. Sprint plan | 1.5 | 1.5 | 0 | On estimate |
| 5. Build, gate and revision | 31.5 | 44.5 | +13.0 | The largest overrun and the most informative. Four causes: the vector store had to be rewritten as pure Python (+2.0), routing had to be rebuilt as ordered gates (+4.0), the safety leaks needed diagnosis rather than a threshold change (+3.0), and model-provider access consumed 4.0 hours for nothing |
| 6. Report, video, packaging | 14.0 | 17.0 | +3.0 | The report ran to 8.0 against 6.0 estimated. Video (6.0) and packaging (2.0) are planned figures, not yet worked |
| Coordinator review | 1.0 | 1.0 | 0 | Held 15 September against a working system |
| Total | 60.5 | 79.5 | +19.0 | A third over. Section 7 says where it went |

# 3  Week one: 6 to 8 September

Discovery, requirements, prompts and planning, plus the first day of the build.

| Date | Task | Stage | Hrs | What it produced | Blocked by anything? |
| --- | --- | --- | --- | --- | --- |
| Sat 6 | Read the pack end to end; mapped the twelve acceptance criteria against the four submission parts | 0 | 2.0 | A one-page map of what is graded and where it is produced | No |
| Sun 7 | Stakeholder interviews read; contradictions between accounts listed rather than resolved | 1 | 2.5 | Five accounts, three explicit disagreements to settle with data | No |
| Sun 7 | Wrote the analysis scripts — answerability by intent, resolution time by segment, effort share vs volume share | 1 | 3.0 | The 70.7% and 47.5% figures; the finding that two intents are never answerable | No |
| Sun 7 | Discovery workbook written up | 1 | 2.5 | Stage_1_Discovery_Workbook_Completed.docx | No |
| Mon 8 | PRD v1.0 — 12 functional, 7 non-functional requirements, each traced to a finding | 2 | 3.0 | Stage_2_PRD_v1.docx | No |
| Mon 8 | Prompt library — 7 versioned prompts with test notes | 3 | 2.5 | prompts/ directory, Stage_3 workbook | No |
| Mon 8 | Sprint plan, two phases around the 15 Sept coordinator review | 4 | 1.5 | Stage_4_Sprint_Plan_Completed.docx | No |
| Tue 8 | B-01 environment + repo scaffold; first live model call attempted | 5 | 2.0 | Repo structure, config module, CI skeleton | Yes — OpenRouter free tier returned 429 on the first call. Deferred; built the offline path instead |
| Tue 8 | B-02 ingest and normalisation, four channels | 5 | 1.5 | src/ingest.py — never raises; customer name excluded from the object by design | No |
| Week 1 | Week total |  | 20.5 | Stages 1–4 complete, build started |  |

# 4  Week two: 9 to 14 September

The build. The gate cleared on Monday 14 September, one day ahead of the coordinator review.

| Date | Task | Stage | Hrs | What it produced | Blocked by anything? |
| --- | --- | --- | --- | --- | --- |
| Wed 9 | B-02 finished; invisible-character and empty-body handling | 5 | 2.5 | Ingest tests green, 580/580 normalise with zero warnings | Yes — my own test file contained literal null bytes and would not parse. 30 min lost |
| Thu 10 | B-03 chunking — section-aware vs fixed 800-char window, measured | 5 | 2.5 | 87.7% vs 85.4% hit@1; section-aware chosen and the reason recorded | No |
| Fri 11 | B-04 retrieval. Vector store abandoned; TF-IDF written in pure Python | 5 | 2.5 | src/retrieve.py, 145 passages, synonym expansion | Yes — chromadb and sentence-transformers would not install. Rewrote rather than fought it |
| Sat 12 | Retrieval threshold sweep, 0.00 to 0.40 across 500 tickets | 5 | 1.5 | Precision caps at 78% at every value. Architectural finding, not a tuning result | No |
| Sat 12 | B-06 classifier, 22 intents; B-07 routing; B-10 decision logging | 5 | 6.5 | End-to-end run on 20 tickets, every decision carrying a reason | No |
| Sun 13 | B-08 generation with citations; B-09 both guardrail layers | 5 | 4.0 | src/generate.py, src/guardrails.py — five deterministic checks | No |
| Sun 13 | Diagnosed 23 safety leaks. Read all 23; found three classifier defects | 5 | 3.0 | Three detectors added, safety intents weighted; violations to zero without touching the threshold | No |
| Sun 13 | B-05 harness computing real metrics | 5 | 2.0 | evaluation/harness.py with --input/--output | No |
| Mon 14 | B-11 THE GATE — full 580-ticket unattended run | 5 | 1.0 | 580/580, 0 errors, 2,490 decisions reconciling, 2.7 s | No |
| Mon 14 | Induced provider outage; found and fixed the retry-storm | 5 | 1.5 | Circuit breaker. 20 tickets from 23 s back to seconds | No |
| Week 2 | Week total |  | 27.0 | Gate cleared one day ahead of plan |  |

# 5  Week three: 15 to 20 September

Review, the Phase B documents, and packaging. The last two rows are planned rather than recorded, and are marked as such.

| Date | Task | Stage | Hrs | What it produced | Blocked by anything? |
| --- | --- | --- | --- | --- | --- |
| Tue 15 | B-18 test suite, B-19 clean-checkout verification, B-14 fairness segmentation | 5 | 2.5 | 62 tests under one command; three fairness gaps found and kept | Yes — SQLite 'disk I/O error' on the second machine; added a temp-dir fallback |
| Tue 15 | Coordinator review held against measured results | — | 1.0 | Discussion on merit rather than on intentions | No |
| Tue 15 | Model provider access — Mistral key configured, tested, failed, re-tested | 5 | 4.0 | Nothing assessable. Account-level block, not a rate limit | Yes — this is the four hours that produced nothing. See section 7 |
| Tue 15 | Fixed the misleading 'no API key configured' error found during the above | 5 | 0.5 | has_key and has_http_library separated, each with its specific fix | No |
| Wed 16 | B-16 PRD v2.0 and the Stage 5 revision log | 5 | 2.5 | 4 requirements changed, 2 added; every entry names a measurement | No |
| Wed 16 | B-17 governance framework — register, fairness audit, incident procedure | 5 | 2.5 | Governance_Framework_Completed.docx | No |
| Wed 16 | Kill switch built, because writing the governance doc found it missing | 5 | 1.5 | src/kill_switch.py + 8 tests including fail-closed. Test count 62 → 78 | No |
| Thu 17 | B-15a report — five figures generated from the measured data; sections 1 to 6 drafted | 6 | 4.0 | Draft through Implementation; Figures 1 to 5 | No |
| Fri 18 | B-15a report — sections 7 to 10, five appendices, contents and cross-references | 6 | 4.0 | RajarajanVenkatesan_Capstone_Report.pdf, 30 pages | No |
| Fri 18 | Effort log reconstructed from the daily learning log and progress tracker | 6 | 1.0 | This document | No |
| Fri 18 | B-13 continuous integration verified running with no API key present | 5 | 0.5 | Workflow green on push | No |
| Sat 19 | B-15b video — rehearsal and two takes | 6 | 6.0 | 18–22 min, planned | Not yet done at time of writing |
| Sun 20 | B-15c packaging and final checklist | 6 | 2.0 | Submission archive | Not yet done at time of writing |
| Week 3 | Week total |  | 32.0 | Phase B documents complete; video and packaging remain |  |

# 6  Estimates against reality

The six largest items from the sprint plan.

| Item | Est. | Actual | Why the difference |
| --- | --- | --- | --- |
| B-15b Video | 6.0 | 6.0 (planned) | Not yet recorded. Two takes are planned, which is what the estimate assumed |
| B-15a Report | 6.0 | 8.0 | Underestimated by a third. Thirty pages of continuous prose with every claim traced to a measurement is slower than thirty pages of description. The figures were quick because the data was already computed |
| B-11 The gate | 4.0 | 1.0 | Four times faster than estimated, because the harness and the offline path were already right. The estimate assumed debugging during the run; there was none. This is the clearest case of earlier work paying for later work |
| B-08 Generation | 3.0 | 3.0 | On estimate, because the prompt was written in Stage 3 before any code existed. The plan predicted this saving and it held |
| B-09 Guardrails | 3.0 | 4.0 | One hour over, spent replacing a length heuristic with claim-marker detection after finding that short replies do make claims |
| B-07 Routing | 2.5 | 6.5 | Two and a half times over, and the most valuable overrun in the project. The estimate covered deriving a threshold. What it actually took was discovering that a threshold cannot carry the decision, and rebuilding routing as four ordered gates |
| B-04 Retrieval | 2.0 | 4.0 | Double. The estimate assumed a vector store that installs. It did not, and TF-IDF with synonym expansion was written from scratch |

# 7  Where the time went unexpectedly

| Question | Answer |
| --- | --- |
| Which task took far longer than you expected, and why? | Routing, at 6.5 hours against 2.5. The estimate was for deriving a confidence threshold from the development data, which is an afternoon of analysis. What it became was the discovery that no threshold can separate answerable tickets from unanswerable ones — feature requests score higher than genuinely answerable tickets — followed by rebuilding routing as four ordered gates with safety ahead of confidence. The overrun was the project working correctly: the plan was wrong about the problem, and the extra four hours are what found that out. Diagnosing the twenty-three safety leaks inside that same stage cost another three hours and followed the same pattern. |
| Which task was easier than you expected, and why? | The gate run, at 1.0 hour against 4.0. The estimate assumed the usual pattern of starting an unattended run and debugging it when it stops halfway. It did not stop: 580 tickets, 2.7 seconds, zero errors, first attempt. That was bought earlier — the ingest layer that never raises, the harness built against the real input contract, and the decision log wired through every stage from the start. Four hours of estimate turned into one because the work had already been done somewhere else. The Stage 3 prompt library did the same thing for generation. |
| What would you allocate differently if you started again on Monday? | Two changes. First, build the evaluation harness before the components rather than alongside them. Every significant correction in this project came from a measurement — the chunking comparison, the threshold sweep, the three classifier defects, the circuit breaker — and each had to wait until something could be run over the full set and scored. Earlier measurement would have surfaced them sooner and more cheaply. Second, timebox infrastructure that earns no marks. Four hours went to model-provider access; a ninety-minute limit would have cost nothing and saved two and a half hours. |
| What did you spend time on that turned out not to matter? | Obtaining working model-provider access, at four hours on 15 September. The graded system was finished and passing at the time, and the pack is explicit that a well-built system on a small free model outscores a thin one on an expensive one. Each step had a plausible next hypothesis — pace the requests, widen the retry budget, correct the model identifier, switch provider — which is exactly how that kind of time disappears. The account was blocked at account level, not rate-limited, and no amount of client-side work was ever going to fix it. Two things were salvaged: the request-pacing and circuit-breaker code is genuinely useful, and the misleading error message found while debugging was a real defect that would have cost someone else the same evening. |

# 8  Declaration

I confirm that this record is an accurate account of my own work on this project, assembled from daily records kept in the repository as the work happened.

| Full name | Signature | Date | Total hours recorded |
| --- | --- | --- | --- |
| Rajarajan Venkatesan | R. Venkatesan | 18 September 2026 | 79.5 (71.5 worked, 8.0 planned) |